## Sheet1
Project Name Backlog
Members: | Sunny, Anna, Abraham, Yousef
Task | Description | Priority | Member | Status | Start Date | Complete Date | Comments
Brainstorm Ideas | Each of us come up w/ a few ideas of projects were interested in | 4 | All | Completed | 2022-03-08 | 2022-03-16
Research Projects | After coming up with ideas, research what we need to learn outside of class | 4 | All | Completed | 2022-03-08 | 2022-03-16
Set up Environment | Download unity hub: https://unity.com/download, android environment setup: https://docs.unity3d.com/Manual/android-sdksetup.html | 4 | All | Completed | 2022-04-06 | 2022-04-07
Design moble game UI | Design UI on Unity | 4 | All | Completed | 2022-04-01 | 2022-04-22
Learn Unity | Watch tutorials on Youtube | 4 | All | Completed | 2022-03-16 | 2022-04-22
Github | Set up Github Repository | 4 | Anna | Completed | 2022-04-06 | 2022-04-06
Wire Diagram | Create wireframes | 4 | Yousef | Completed | 2022-04-06 | 2022-04-22
Implement Joystick | Allow character movement using joystick | 4 | Anna | Completed | 2022-04-10 | 2022-04-30
Start/Main Menu | Create main menu of game (first page user will see) | 3 | Sunny | In Progress | 2022-04-26
Implement Attack Button | Allow character to attack enemies | 4 | Anna | Completed | 2022-04-30 | 2022-04-30
Implement Skills Menu | Create a popup menu for leveling up skills | 3 | Abraham | Not Started
Finishing Screen | For when user wins/finished the game | 4 | Anna | Completed | 2022-05-09 | 2022-05-09
Enemy Creation | Game Logic | 4 | Yousef | Completed | 2022-04-10 | 2022-04-20
Damage/HP Creation | Game Logic | 4 | Yousef | Completed | 2022-04-11 | 2022-04-21
Movement | Game Logic | 4 | Yousef | Completed | 2022-04-12 | 2022-04-22
Implement Jump Button | Allow character to jump | 4 | Anna | Completed | 2022-04-30 | 2022-04-30
Restruct project to top level | Restruct project to top level and remove built files to avoid merge conflicts | 4 | Anna | Completed | 2022-04-30 | 2022-04-30
Help with merge conflicts | Solve merge conflicts | 3 | Anna | In Progress | 2022-05-03
Create Home Menu Background | Background for main menu from photoshop image | 2 | Yousef, Sunny | In Progress | 2022-05-03
Character Select Menu | List of possible characters player can unlock | 2 | Yousef, Sunny | In Progress | 2022-05-03
Monster/Enemy Pokedex | List of enemies player has defeated | 2 | Yousef, Sunny | In Progress | 2022-05-03

## Utils (hidden)
Priority | Status | Member | All | Sunny | Anna | Abraham | Yousef
1 | Waiting
2 | Not Started
3 | In Progress
4 | Completed